## NexusHealth_Defect_Report
Defect ID | Project Name | Module | Requirement ID | Test Case ID | Defect Summary | Defect Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Defect Type | Environment | Reported By | Reported Date | Assigned To | Status | Root Cause | Fix Version | Retest Date | Retest Result | Closed By | Closure Date | Attachments | Module Category
NPH-15 | Nexus Health | Claims |  |  |  | 132 claims records are present in Claims table | but no pagination available | user cannot find particular claim. |  |  | High | High | Functional | QA | Usha Raman | 2026-06-12 |  | To Do | [6 empty] | https://lakshmi199.atlassian.net/browse/NPH-15 | Admin
NPH-14 | Nexus Health | Login/Session |  |  |  | Back Button Shows Admin Page After Logout |  |  | Medium | Medium | Security | QA | integration | 2026-06-11 |  | To Do | [6 empty] | https://lakshmi199.atlassian.net/browse/NPH-14 | Admin
NPH-13 | Nexus Health | Patient Profile |  |  |  | Phone number field accepts alphanumeric characters and more than 10 digits. Validation missing. |  |  | Medium | Medium | Validation | QA | integration | 2026-06-11 |  | To Do | [6 empty] | https://lakshmi199.atlassian.net/browse/NPH-13 | Patient
NPH-12 | Nexus Health | Login Security |  |  |  | Account Not Locked After 5 Invalid Login Attempts |  |  | Medium | Medium | Security | QA | integration | 2026-06-11 |  | To Do | [6 empty] | https://lakshmi199.atlassian.net/browse/NPH-12 | Admin
NPH-11 | Nexus Health | Patient Module |  |  |  | Invalid input validation issues in Edit Profile page (First Name | Last Name | Phone | Email | DOB fields) |  |  | integration | Highest | Validation | QA | LK | 2026-06-11 |  | In Progress | [6 empty] | https://lakshmi199.atlassian.net/browse/NPH-11 | Patient
NPH-10 | Nexus Health | Patient Registration |  |  |  | Patient Registration Form Accepts Invalid and Inconsistent User Input Without Validation |  |  | High | High | Validation | QA | integration | 2026-06-09 | LK | In Progress | [6 empty] | https://lakshmi199.atlassian.net/browse/NPH-10 | Patient
NPH-4 | Nexus Health | Session Management |  |  |  | Logging out in one tab logs out other user |  |  | Highest | Highest | Security | QA | integration | 2026-06-05 |  | In Review | [6 empty] | https://lakshmi199.atlassian.net/browse/NPH-4 | Admin
NPH-5 | Nexus Health | Appointments Overview |  |  |  | Pagination missing in Appointments Overview screen |  |  | High | High | Functional | QA | integration | 2026-06-05 |  | In Review | [6 empty] | https://lakshmi199.atlassian.net/browse/NPH-5 | Admin
NPH-9 | Nexus Health | Messages |  |  |  | Messages table layout breaks on mobile devices |  |  | Medium | Medium | UI/Responsive | QA | integration | 2026-06-05 |  | In Progress | [6 empty] | https://lakshmi199.atlassian.net/browse/NPH-9 | Admin
NPH-8 | Nexus Health | Patients Page |  |  |  | Unauthorized users can access Patients page without login |  |  | High | High | Security | QA | integration | 2026-06-05 |  | In Progress | [6 empty] | https://lakshmi199.atlassian.net/browse/NPH-8 | Admin
NPH-7 | Nexus Health | Admin Home |  |  |  | Unauthorized users can directly access Admin Home page without login |  |  | High | High | Security | QA | integration | 2026-06-05 |  | In Progress | [6 empty] | https://lakshmi199.atlassian.net/browse/NPH-7 | Admin
NPH-6 | Nexus Health | Admin Module Access |  |  |  | Doctor user can access Admin Module pages despite role-based access restrictions |  |  | High | High | Security | QA | integration | 2026-06-05 |  | In Progress | [6 empty] | https://lakshmi199.atlassian.net/browse/NPH-6 | Doctor
NPH-3 | Nexus Health | Admin Module Access |  |  |  | Patient User Can Access Admin Pages Directly via URL |  |  | High | High | Security | QA | integration | 2026-06-04 |  | In Progress | [6 empty] | https://lakshmi199.atlassian.net/browse/NPH-3 | Patient
NPH-2 | Nexus Health | Login Security |  |  |  | Application allows unlimited failed login attempts without account lockout |  |  | Medium | Medium | Security | QA | integration | 2026-06-04 |  | In Progress | [6 empty] | https://lakshmi199.atlassian.net/browse/NPH-2 | Admin
NPH-1 | Nexus Health | Login |  |  |  | Login page not accessible when accessing application URL |  |  | Highest | Highest | Functional | QA | integration | 2026-06-03 |  | In Progress | [6 empty] | https://lakshmi199.atlassian.net/browse/NPH-1 | Admin